Guide2. APT Project Development

Capstone Subject

1. Summary of APT Project Progress

Below, you will find different fields that you must fill in with the requested information.

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competence or units of competences | Activities | Resources | Duration of the activity | Responsible | Remarks | Progress status | Settings |
| Project Management | Requirements Survey | Recordings, meetings | 1 week | Elijah | Promotes accuracy, builds trust with the community | Completed | None. It is the basis for development. |
| Database Modeling | DB Design (DER, Standardization, and Documentation) | Draw.io, MySQL | 2 weeks | Yerko | The logical model is required to move to implementation. | Completed | None. |
| Database Modeling | Creating the Physical Model (backup.sql) | MySQL Workbench, SGBD chosen | 1 week | Yerko | PRIORITY: It is the executable script. Necessary for Fabián to start the backend. | Current | It is defined as blocking and immediate activity from the DER. |
| Software Architecture | Architecture Definition (Offline-First) | Draw.io, Lucidchart, Documentation | 1 week | Elijah | The hybrid architecture should guide the data synchronization logic. | Current | The need for the hybrid offline-first model for system resilience is formalized. |
| UI/UX Design | Refinement to High Fidelity Prototype | Figma (Link), Mockup Codebase | 1 week | Yerko | FACILITATOR: The existence of the mockup in Figma speeds up this step. DIFFICULTY: Requires final validation of the APR. | Adjusted | It goes from static mockup to functional interactive prototype for usability validation. |
| Project Management | Git Repository Creation and Configuration | Git, GitHub/GitLab | 0.5 weeks | All Team | ABSOLUTE PRIORITY: Allows simultaneous collaboration and version control. | Not started | It is added as a pre-encoding blocking activity. |
| Software Development | Billing Module - Backend (API) | Node.js (Express), MySQL, Postman | 2 weeks | Fabián | DIFFICULTY: Weekly review of endpoints. It depends entirely on the Physical Model (backup.sql) generated by Yerko. | Current | It starts with the API design (schemas and paths) waiting for the DB DDL. |
| Software Development | Billing Module - Frontend (Views) | React/IONIC, Mockup Codebase | 1 week | Yerko | DIFFICULTY: It depends on the Backend API being stable to make data requests. | Not started | Dependence on Fabián's backend is maintained. |
| Software Development | Online Payments Integration | WEBPAY API (or other), Documentation | 2 weeks | Elijah | DIFFICULTY: Possible reliance on sandbox testing and legal/technical requirements of the payment gateway. | Not started | It is maintained. |
| Software Development | Alert System | Firebase, API REST | 1 week | Fabián | DIFFICULTY: Depends on connectivity and well-defined notification endpoints. | Not started | It is maintained. |
| QA/Quality Management | Unit Tests | Jest, Postman, Simulated Dataset | 1 week | Yerko | DIFFICULTY: It is required to create a simulated dataset that covers billing limit cases. | Not started | It is maintained. |
| QA/Quality Management | Integration Testing | Test Environment (Local Server) | 1 week | Fabián | DIFFICULTY: Requires all modules to be functional to verify interaction. | Not started | It is maintained. |
| QA/Quality Management | User testing | Real data (controlled) | 1 week | Elijah | DIFFICULTY/RISK: Possible resistance to change on the part of APR users. | Not started | It is maintained. |
| Project Management | Preparation of manuals | Word, Canva, PPT | 1 week | Fabián | Prior teacher review. | Not started | It is maintained. |
| Project Management | Staff training | Manuals, PPT | 1 week | Yerko | FACILITATOR: The interactive prototype helps with training. | Not started | It is maintained. |
| Project Management | Initial deployment | Local Server + Hosting | 1 week | All Team | Post-implementation monitoring. | Not started | It is maintained. |

| APT Project Progress Summary | During the development of the APT project, significant progress has been made in several of the planned activities. In this stage, the following elements were completed: the database model, developed by Yerko, together with the mockups of the system and requirements survey, developed by Fabián, both marked as completed (or in development) and context diagram by Elias. These deliverables represent an important step forward, as they allow for clearer definition of the structure of the information and the design of the user interface. Currently, the generation of the backup.sql file, also in charge of Yerko, for the backup and deployment of the database is pending. On the other hand, Elias continues with the architecture model, which is under development, while the deployment model has not yet been started. Finally, the Git repository also remains pending, a fundamental step to centralize version control and team collaboration. So far, the specific objectives associated with the definition of the data model and the visual presentation of the system have been met. There have been no major adjustments to the objectives or methodology, although improvements are planned to be made to the organization and management of the repository to optimize the workflow in the next stages. |
| --- | --- |
| Evidence of progress | In this report, two main evidences are presented: the database model and the mockup. The database model shows how the information will be organized in the system, while mockups offer a clear idea of the design and interface that the user will have. This evidence reflects the real progress in the project, showing that key technical and visual parts have already been defined. |
| 2. Monitoring of the Work Plan |
| Carefully examine your work plan, focusing especially on the progress status and adjustments column. |

3. Adjustments from monitoring

Dig deeper into the observations in your work plan. It analyses the planned activities and points out which aspects facilitated or hindered the execution of the plan. Discuss how you addressed and/or will address the obstacles. Finally, point out the adjustments you made to the work plan based on this analysis.

Factors that have facilitated and/or hindered the development of my work plan: A factor that has facilitated the development of the project is the communication within the team, which allowed us to resume and advance in the activities when it was executed well. However, the lack of constant supervision and follow-up by ourselves negatively affected progress, leading to delays and incomplete activities. To solve these difficulties, it is planned to reactivate communication and interactions within the team, better organizing tasks and times according to the Gantt chart. Regular meetings will be held to monitor progress and support those who have problems, thus seeking to maintain the efficient workflow and detect obstacles in time. This reflection has made it possible to identify the importance of more constant supervision and better coordination so that the team can meet the objectives in the established times.

Activities adjusted or eliminated: So far, some adjustments have been made to the work plan mainly due to delays in monitoring and tracking activities. Some tasks have been rescheduled to better accommodate times and ensure the delivery of products such as the backup.sql file and the deployment model, pending until now.

Activities that you haven't started or are delayed: Activities that haven't started yet or are delayed are primarily the backup.sql file and deployment model, as well as the creation of the Git repository. To move forward and prevent these delays from affecting the project, the following strategies will be implemented: activate regular follow-up meetings to monitor progress, better organize tasks with clear times in the Gantt chart, encourage continuous communication within the team, and provide immediate support to those facing difficulties, these actions will help make up for lost time and ensure that the APT project meets the established deadlines.

In the event that the APT Project is a group project, in this column they must indicate the name of those responsible for each task or activity. This will later allow differentiating the evaluation by each member.